## Sheet1
Release 2 Smart Schedule Estimate
|  |  | Sergei | Boris
1 | Move logic from client to server |  | 80 | 30
2 | Modify client to work with server. Release to dispatch for use |  | 40 | 15
3 | New functionality
| 3.1 | Multi Day support | 60 | 25
| 3.2 | Multi Day configuration for dispatcher | 30 | 10
| 3.3 | Multiday Recommendations | 40 | 12
| 3.5 | Bucket Limit and Area Management | 40 | 15
4 | Integration with Servman |  | 40 | 25
5 | Current support of smart schedule, bug fixes |  | 40 | 20
6 | Meetings, testing |  |  | 50
| Total Hours |  | 370 | 202
| Estimated Start Date |  |  | 2010-01-31
| Estimated Completion Date |  |  | 2010-03-27