## Sheet2
Release 3 Smart Schedule Estimate
|  |  | Sergei | Boris | Esimated Delivery Date
1 | Multi Day support |  | 16 | 4 | 2010-06-14
| 1.1 | Servman continuus update
| 1.2 | Select date on dashboard and show only info for this date
| 1.3 | Dashboard update for specific date
2 | Develop intefaces with Servman, Web Site |  | 8 | 2 | 2010-06-15
| 2.1 | Develop inteface for technician settings modification
| 2.2 | Develop interface for recommedations
3 | Multiday support for technician settings |  | 80 | 20 | 2010-06-29
| 3.1 | Develop process so that daily and default setting can be modified
| 3.2 | Develop UI for dispatcher for midify technician settings
| 3.3 | Work with Wayne to integrate it into intranet
4 | Multiday Recommendations |  | 28 | 8 | 2010-07-02
| 4.1 | Modify recommendation algorithm to take cost into account | 24
| 4.2 | Adjust interface between SmartSchedule and Servman | 4
5 | Intergaration of recommendation with Servman and Web Site |  | 8 |  | 2010-07-05
| 5.1 | Desing an interface of communication between Servman and Smart Schedule
| 5.2 | Integrate with web site
6 | Day Optimization Mode |  | 60 | 20 | 2010-07-15
| 6.1 | Background optimization mode processing with concurrent predictions
7 | Release, deployment, issue resolution |  | 20 | 30 | 2010-07-20
7 | Current support of smart schedule, bug fixes |  | 40 | 8
8 | Meetings, testing |  |  | 50
| Total Hours |  | 260 | 142
| Estimated Completion Date |  |  | 2010-07-20
| Start Date |  |  | 2010-06-10