## 2011-0626-0709
date | person | hours | description | todo | list | company | project
2011-07-01 | Valery Yaworsky | 1 |  | Add filter to business partner based on sales rep | Misc | Dalworth Restoration | Lead Central
2011-07-01 | Valery Yaworsky | 3 |  | Add filter to campaign based on business partner, sales rep | Misc | Dalworth Restoration | Lead Central
2011-06-28 | Valery Yaworsky | 3 | Create new methods to platform context for in-app payments | New payment process. Using in-app charge | Misc | Dalworth Restoration | Lead Central
2011-07-08 | Valery Yaworsky | 2 |  | Deploymeent / testing | Release 1.0 | Dalworth Restoration | Lead Central
2011-07-05 | Valery Yaworsky | 3 | review / testing | Deploymeent / testing | Release 1.0 | Dalworth Restoration | Lead Central
2011-07-04 | Valery Yaworsky | 0.5 |  | Deploymeent / testing | Release 1.0 | Dalworth Restoration | Lead Central
2011-07-01 | Valery Yaworsky | 1 |  | review | Release 1.0 | Dalworth Restoration | Lead Central
2011-07-01 | Valery Yaworsky | 1 |  | Graph on home page is not working on IE | Release 1.0 | Dalworth Restoration | Lead Central
2011-07-01 | Valery Yaworsky | 2 | deployment | Deploymeent / testing | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-30 | Valery Yaworsky | 3 |  | block incoming phone number | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-30 | Valery Yaworsky | 2 | UI changes | Add functionality to disable business partner | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-30 | Valery Yaworsky | 2.5 |  | Add functionality to disable business partner | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-30 | Valery Yaworsky | 0.5 |  | Test partner. Same as real partner but not in reports | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-29 | Valery Yaworsky | 0.5 |  | Add functionality to disable business partner | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-29 | Valery Yaworsky | 0.5 |  | Add address to business partners. They use it to keep information about them. | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-29 | Valery Yaworsky | 2 |  | In Lead Screen, add filter by sales rep, business partner, remove by caller id | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-29 | Valery Yaworsky | 6 |  | Remove long process from twilio web service | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-28 | Valery Yaworsky | 0.5 |  | Test partner. Same as real partner but not in reports | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-28 | Valery Yaworsky | 0.5 |  | block incoming phone number | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-28 | Valery Yaworsky | 1.5 |  | Add address to business partners. They use it to keep information about them. | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-28 | Valery Yaworsky | 0.5 |  | Look at twilio debug tools make sure we handle all calls. | Release 1.0 | Dalworth Restoration | Lead Central
2011-06-28 | Valery Yaworsky | 2 |  | Remove long process from twilio web service | Release 1.0 | Dalworth Restoration | Lead Central
2011-07-05 | Valery Yaworsky | 1 |  | Receive SMS problem / testing | Release 1.1 | Dalworth Restoration | Lead Central
2011-07-05 | Valery Yaworsky | 1 |  | http://phone.theleadcentral.com/CommitDial.ashx?realmId=182801782 Still getting 502 error | Release 1.1 | Dalworth Restoration | Lead Central
2011-07-04 | Valery Yaworsky | 0.5 |  | creates clean db script saying release 1.1 that has all mysql db | Release 1.1 | Dalworth Restoration | Lead Central
2011-07-04 | Valery Yaworsky | 0.5 |  | Accounter role should say Accountant | Release 1.1 | Dalworth Restoration | Lead Central
2011-07-04 | Valery Yaworsky | 0 |  | create sql server backup with diagrams and check it in into vault | Release 1.1 | Dalworth Restoration | Lead Central
2011-07-04 | Valery Yaworsky | 1 |  | Test create customer db | Release 1.1 | Dalworth Restoration | Lead Central
2011-07-04 | Valery Yaworsky | 2 |  | http://phone.theleadcentral.com/CommitDial.ashx?realmId=182801782 Still getting 502 error | Release 1.1 | Dalworth Restoration | Lead Central
2011-07-08 | Valery Yaworsky | 6 |  | notifications | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-07 | Valery Yaworsky | 2 | UI for review on campaign profile | notifications | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-07 | Valery Yaworsky | 3 | db, domain, service | notifications | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-07 | Valery Yaworsky | 3 |  | Create in App payment screens | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.25 |  | Create new campaing - add link to business partner. | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.25 |  | Create new campaign - default sales rep for BP sales rep if came from business partner | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.5 |  | new user - save, cancel. remove link to user list | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.25 |  | new user - show partner | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.5 |  | Create new campaign - add cancel button. Come back to partner or list of campaign, depending how we got there. | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 1 |  | users list - show active, all option | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 1 |  | on business partner detail, add list of tracking phones assigned to campaing | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 1 |  | remove all test leads (cancel) | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.75 |  | add contact phone, show business partner info and link to come back to bp | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.25 |  | phone details , add assigned campaign. Link to go to campaign | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0 |  | in campaign detail say "Tracking Phones" instead of assign phone numbers | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.25 |  | campaign list, business partners must be sorted. | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.25 |  | modify flow to to create campaign form partner | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.25 |  | modify flow to create user from partner | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.25 |  | Search by sales rep did not find a campaign | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.5 |  | add call duration to lead list. Make duration show minutes and seconds. | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0 |  | remove bread crums | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0 |  | All assigned phone numbers will be removed from current Campaign. Add be between will and removed | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 1.5 |  | Black list right from lead . Ask "Are you sure" ? | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-06 | Valery Yaworsky | 0.5 |  | Tracking phone. Format phone number | Release 1.3 | Dalworth Restoration | Lead Central
2011-07-04 | Valery Yaworsky | 2 |  | Add campaign from business partner | Release1.2 | Dalworth Restoration | Lead Central
2011-07-04 | Valery Yaworsky | 2.5 |  | Add user from business partner | Release1.2 | Dalworth Restoration | Lead Central
15
72.25
1083.75