## Sheet2
Agent Intranet Project Plan
|  |  | Sergei | Boris | Esimated Delivery Date
|  | Rate | 30 | 60
1 | Setup and Complete requirement document |  | 27 | 16 | 2011-03-24
| 1.1 | Setup development environment, compile code | 6 | 6
| 1.2 | Research trouble ticket workflow and update document | 6 | 2
| 1.3 | Design mockup for page 7 signup | 3 | 1
| 1.4 | Design final mockup for exisitng customer page | 3 | 1
| 1.5 | Add trouble ticket management into exising customer page mockup | 3 | 1
| 1.6 | Research workflow of minute replanishment and modify mockups | 5 | 2
| 1.7 | Discuss and prove final requiremetn document and hours with Overgoup | 1 | 3
2 | Implement sing, print, sign and print |  | 36 | 7 | 2011-04-01
| 2.1 | Implement sing and print on page of singup screen | 24 | 4
| 2.2 | Implement sing and print on exising customer screen | 12 | 3
3 | Implement trouble ticket functionality |  | 24 | 6
4 | Implement minute replanishment |  | 32 | 8 | 2011-04-12
5 | Meetings, testing, acceptance |  | 6 | 12 | 2011-04-13
| Total Hours |  | 125 | 49
| Estimated Amount |  | 3750 | 2940
| Total Amount |  | 6690
Estimated Completion Date
Start Date