## Sheet1
# | Task | Est | Act | Start | End | Status
1 | Meetings |  | 1
| Jun 17 - 10:00 to 11:00 EST |  | 1
2 | Mapping and Drawing functions | 12
2.1 | Multiple locn maps - business, segment, client pages | Affilia | EBS | =============== Notes ====================
Summary page map display:
| No pan or zoom. | yes |  | 2010-06-17 | Resolved | Fix
Markers shown and clickable
Info windows with facility name, address, city, province
Double click for full screen.
Maps display correct facilities based on invoking screen
Maps handle facilities with no location data - no marker displayed
Display same content as the zoom map
Changes immediately applied when full screen closed after Edits
Full screen display:
Exit button displayed, botton right, closes screen.
Optional Edit button, to left of Exit, set based on property
No pan, zoom; markers show info windows
Markers with info windows, as on summary screen
Edit Window:
Enables zoom and pan
Displays Save and Cancel buttons. (Only)
Window closes on save or cancel, returns to full screen window
2.2 | Single locn map - facility page
As above, but shows marker for current facility only, and allows
for marker create and positioning as part of Edit screen.
Edit Window:
"Create Facility Marker" button - places marker at map center.
Edit allows marker moves
Save updates marker position (plus map pan and zoom)
Marker position updated on return to Summary screen
2.3 | Site Plan - facility page
As above for setting position and zoom.
Does not show facility marker
Summary screen responds to layer selection.
Full screen displays same layer selections.
Layer selections retained when new facility selected
2.4 | Site Plan - section page
No Edit function to set pan and zoom (done from facility page)
Shades the selected roof section
2.5 | Roof Plan - section page
Edit Window:
Displays Create Roofplan, Edit roofPlan, Save and Cancel
These first 2 buttons are toggle buttons
Save to update all changes - position, zoom and polygons
Cancel to discard all changes to position and polygons
Drawing functions
No changes
3 | Condition Report and related screens
4 | Remaining Grids and Forms
5 | Inspections
6 | Aegis Data Conversion
7 | IPP Deployment (optional)
Note on D12: Jim Maybee: This is the time from 10:00 EST onward.
Note on H15: Jim Maybee: affilia to fix
Note on H16: Jim Maybee: this is a big asd asd asd asdasdasd asd asd asd asd ad asd asd asd
Note on H18: Jim Maybee: Major problem

## Sheet2
Usage Notes
- Tasks created for all work done by Affilia.
- All hours billed through time sheets to include the task number.
- Project status to be updated