## Sheet2
Usage Notes
- Tasks created for all work done by Affilia.
- All hours billed through time sheets to include the task number.
- Project status to be updated

## 0617-0626
# | Task | Est | Act | Acutal Estimated Left | Start | End | Status
| Totals | 50 | 13
Task management and billing policies
This task list is effective as of June 18 10:00 am EST
All work must appear on this task list before it is approved
Each task must be assigned an estimate
All billable work must reference a task # and match the approved hours
(Approved hours will be added when task is closed)
Invoices have been received that cover all work to June 18 10:00am
A single invoice should be issued to cover work after this time
Daily Builds
Tasks that span multiple days should have daily builds
1 | Meetings | 8 | 1
| Jun 17 - 10:00 to 11:00 EST |  | 1
2 | Mapping and Drawing functions | 12 | 12 |  | 2010-06-17
2.1 | Multiple locn maps - business, segment, client pages | Affilia | EBS |  | Later? | =============== Notes ====================
Summary page map display:
| No pan or zoom. | yes |  |  |  | 2010-06-17 | Resolved | Fix
Markers shown and non-clickable
Info windows with facility name, address, city, province
Double click for full screen.
Maps display correct facilities based on invoking screen
Maps handle facilities with no location data - no marker displayed
Display same content as the zoom map
Changes immediately applied when full screen closed after Edits
Full screen display:
Exit button displayed, botton right, closes screen.
Optional Edit button, to left of Exit, set based on property
No pan, zoom; markers show info windows
Markers with info windows, as on summary screen
Edit Window:
Enables zoom and pan
Displays Save and Cancel buttons. (Only)
Window closes on save or cancel, returns to full screen window.
2.2 | Single locn map - facility page
As above, but shows marker for current facility only, and allows
for marker create and positioning as part of Edit screen.
Edit Window:
"Create Facility Marker" button - places marker at map center.
Edit allows marker moves
Save updates marker position (plus map pan and zoom)
Marker position updated on return to Summary screen
2.3 | Site Plan - facility page
As above for setting position and zoom.
Does not show facility marker
Summary screen responds to layer selection.
Full screen displays same layer selections.
Layer selections retained when new facility selected
2.4 | Site Plan - section page
No Edit function to set pan and zoom (done from facility page)
Shades the selected roof section
2.5 | Roof Plan - section page
Edit Window:
Displays Create Roofplan, Edit roofPlan, Save and Cancel
These first 2 buttons are toggle buttons
Save to update all changes - position, zoom and polygons
Cancel to discard all changes to position and polygons
Drawing functions
No changes
2.6 | Discussion Points
Should the small maps allow pan, zoom?
Should the zoomed zite plan allow layer select?
2B | Mapping and Drawing fixes & revisions | 6 | 5
The segment maps should use consultant.mapcenter, zoomlevel etc.
Implement the Bing functions for Zoom and Pan
- Use the Bing slider on the map, in place of the slider at bottom of screen
- Double click zooms in
- Mouse wheel to move in/ out
Layer selection
- No drawing layer selection on business, segment, and client levels
- Add a layer selection control below the Section roof plan
- The layer selections on the facility and sections screen should be
retained when a new facility/ section is selected.
Size and position
- Set all maps to same size and left position as the facility maps
- Set all photos to the same size and position
Map size and position defaults
- Segments use the consultant settings (as above)
- Clients use the consultant settings as a default
- Facility map and site plan use the client settings as a default
- Roof plan uses site plan settings as default
RoofPlan drawing functions
- Edit Roof Plan doesn't turn off
- When create new poligon, user can only save or cancel. When cancel , all points are gone,When save, autocomplete poligon
without using the point at the button
- clicking on the first point circle icon should close to the start point
not the point clicked on
Misc (more testing required)
- the map position data seems to show in the position field
- The Edit button was not displayed on any map - required shut-down
- The zoomed map seemed to lose the settings.
- the Edit screens seems to partly hang - Save, Close didn't do anything
3 | Base System Completion | 10
3.1 | General |  | Affilia |  | EBS
Data entered on Canceled form is retained on next edit
| The required red asterisk should not show on the view form |  |  |  | Codes
| Do uploads remove storage for any previous uploads? |  |  |  |  | Minor items/ fixes |  | 4 Hours | 43 items - for Monday
| All photos should display without scroll bars |  |  |  |  | Additional |  | 6 Hours | 13 items - for Tuesday
| All photos should retain aspect ratio - fixed width, variable height |  |  |  |  | Future
Changed names don't update to tree
Change "Submit" to "Save" when used on an Add or Edit form
Notes
3.2 | Developer Menu |  |  |  | To save time - I can assist with testing
| Change menu name to "Developer" |  | DONE |  | Notes can added beside each task - Using the Excel Review - New Comment
| Remove "Database Tables" from Developer menu |  | DONE |  | Add the note in the coloured cells, as done in first cell.
3.3 | Tree, Add, Delete |  |  |  | LEGEND
| Remove the title on top border "Aegis Building..." |  | DONE |  |  | - Defects and small fixes - 5 hours
| Change to support multiple consultants - multiple root nodes |  |  |  |  | - Optional, spend 5 hours
| Expand on the arrow prefix only - not on the name |  |  |  |  | - Future
Fix error handling
Options are unclear - retry vs cancel
Displays dimmed box after cancel
Can drop out of application
Add Segment
Validate as Unique
Add Client:
| Add Client not working (Pg 16) |  | DONE
Validate client name unique across all segments
Validate Brief name unique across all segments
Add Facility:
| Add Facility not working (Pg 16) |  | DONE
Validate Facility name unique within the client
Validate Facility brief name unique within the client
Add Section
| Designation as single line text box |  | DONE
Validate Designation unique within the facility
| Change roof name to text input, not select (duplicates allowed) |  | DONE
Delete function
Add to right of Add button
Delete Segment, Client, Facility and Section (not business)
Delete Confirm
Don't allow delete if child records present
3.4 | Business - Summary
| Remove edit button (Company information will be maint using QB) |  | DONE
| Commas in sq ft |  | DONE
| Currency to 0 dec |  | DONE
3.5 | Business - Segments
| Remove form at bottom - display when grid line clicked |  | DONE
| Commas in sq ft |  | DONE
| Commas in currency |  | DONE
3.6 | Business - Map
| Remove (after summary page maps working) |  | DONE
3.7 | Segment - Summary
| Commas in sq ft |  | DONE
| Currency to 0 dec |  | DONE
3.8 | Segment - Clients
| Remove form at bottom - display when grid line clicked |  | NONE
| Commas in sq ft |  | DONE
| Commas in currency |  | DONE
Revise columns
3.9 | Segment - Map
| Remove (after summary page maps working) |  | DONE
3.10 | Clients- Summary
| Commas in sq ft |  | DONE
| Currency to 0 dec |  | DONE
| Complete the client View/ Edit form (design 5.7) |  | DONE
3.11 | Client - Facilities
| Remove form at bottom - display when grid line clicked |  | DONE
Revise columns
3.12 | Client - Map
| Remove (after summary page maps working) |  | DONE
3.13 | Facility - Summary
Additional contacts is editable while in view mode.
Upload error hung the app.
The orange 'in progress' bar didn't go away after upload
3.14 | Facility - Sections
| Remove form at bottom - display when grid line clicked |  | DONE
3.15 | Facility - Map
| Remove (after summary page maps working) |  | DONE
3.16 | Facility - Siteplan
| Remove (after summary page maps working) |  | DONE
3.17 | Facility - Details tab through Warranties tab
Implement as in Design document
3.18 | Facility - Reports
Move the button to the Summary page - Left side - same line as Edit
Remove the Reports tab
Test the condition report content
Test condition page ejects and orphan control
Enhance to support RTF
Enhance to support maps, siteplans and roof plans
Fix the IE problem
Fix the problem on Alistair's computer
3.19 | Section - Summary
Edit form
| Sq Ft - numeric input only - remove incr/ decrement |  | DONE
| Year Installed - remove incr/ decrement |  | DONE
3.2 | Section - Site Plan
| Remove (after summary page site plan working) |  | DONE
3.21 | Section - Roof Plan
| Remove (after summary page roof plan working) |  | DONE
3.22 | Section - System
Core Composition Edit form
| Double the width of all input controls |  | DONE
| Change description to one line |  | DONE
Core Photos Input form
| "Layer type" label --> Date taken |  | DONE
Problem in Edit when a new photo is not uploaded
Delete to remove photo storage
Lost cursor - ok on Intuit menu, not our menu or below!
Overall Core Assement memo
No edit function
3.23 | Section - Core Cuts
| Remove |  | DONE
3.24 | Section - Details
Implement as in Design document
3.25 | Section - Deficiencies
Implement as in Design document
3.26 | Section - Inspections
Edit Form
Change Inspector Company to Text box, not select
| Double the width and height of the assessment memo |  | DONE
Submit didn't respond on Edit form. Cancel worked
Changes not updated - Grid shows prev date.
List in reverse date sequence (latest inspections at top of list)
3.27 | Section - Surveys
Implement as in design document
3.28 | Section - Expenditures
Add/Edit Form
Remove incrementor on budget year
Double the width and height of the details of activity memo
Submit didn't respond (same as inspections)
Error on Type of Activity - Too long (I selected one of the values!)
Edits not saved - same as inspections
3.29 | Section - Warranties
Implement as in Design document
3.3 | Analysis Menu
Implement as in Design document
4 | Inspections | 12
iPhone data capture
| Get authenticate and API_AddRecord working (Affilia) | 2 | 5 | 0
Establish iPhone software delivery process
Test IPP authenticate and upload from iPhone
Test voice, photo and GPS upload
Complete 2-3 prototype designs
| Inspection page | 15 | 14 | 1
Revise inspection fields -as in design spec
Photo upload and annotation entry
Marker placement
On Inspection, show read only project Name
On Actitities, project name and ispection id
On Photos, project Name
| Pro-Spec report | 12
Code the report - as in design specs
| Dictation | ?
Flex payback with foot pedal
5 | Roles, permissions, user management | 4
6 | Deployment, entitlements, pricing | 4
7 | Future
Aegis Data conversion
Tasks
Note on J22: Jim Maybee: affilia to fix
Note on J23: Jim Maybee: this is a big asd asd asd asdasdasd asd asd asd asd ad asd asd asd
Note on J25: Jim Maybee: Major problem
Note on D32: Valery Yaworsky: Edit button is available for all users
Note on D38: Valery Yaworsky: Cancel button restore previous map state
Note on D107: Jim Maybee: Same note