## Sheet1
# | Task | Est | Act | Start | End | Status
| Notes | 48 | 1
Task management and billing policies
This task list is effective as of June 18 10:00 am EST
All work must appear on this task list before it is approved
Each task must be assigned an estimate
All billable work must reference a task # and match the approved hours
(Approved hours will be added when task is closed)
Invoices have been received that cover all work to June 18 10:00am
A single invoice should be issued to cover work after this time
Daily Builds
Tasks that span multiple days should have daily builds
1 | Meetings | 8 | 1
| Jun 17 - 10:00 to 11:00 EST |  | 1
2 | Mapping and Drawing functions | 12 |  | 2010-06-17
2.1 | Multiple locn maps - business, segment, client pages | Affilia | EBS | Later? | =============== Notes ====================
Summary page map display:
| No pan or zoom. | yes |  |  | 2010-06-17 | Resolved | Fix
| Markers shown and Not clickable | yes
| Double click for full screen. | yes
| Maps display correct facilities based on invoking screen | yes
| Maps handle facilities with no location data - no marker displayed | yes
| Display same content as the zoom map | yes
| Changes immediately applied when full screen closed after Edits | yes
| Full screen display: | yes
| Exit button displayed, botton right, closes screen. | yes
| Optional Edit button, to left of Exit, set based on property | Yes
| No pan, zoom; markers show info windows | yes
| Markers with info windows, as on summary screen | No
| Info windows with facility name, address, city, province | Yes
Edit Window:
| Enables zoom and pan | yes
| Displays Save and Cancel buttons. (Only) | yes
| Window closes on save or cancel, returns to full screen window | yes
2.2 | Single locn map - facility page
| As above, but shows marker for current facility only, and allows | yes
| for marker create and positioning as part of Edit screen. | yes
Edit Window:
| "Create Facility Marker" button - places marker at map center. | yes
| Edit allows marker moves | yes
| Save updates marker position (plus map pan and zoom) | yes
| Marker position updated on return to Summary screen | yes
| BUG: Map center with Field ID 73 too long when moving a marker | yes
| BUG: On facility level, can move facility in read only mode | yes
2.3 | Site Plan - facility page
| As above for setting position and zoom. | yes
| Does not show facility marker | yes
| Summary screen responds to layer selection. | yes
| Full screen displays same layer selections. | yes
| Layer selections retained when new facility selected | yes
| BUG: Moved marker, save, got a bug Map center field is too long (Try Sears, Brentwood) | yes
2.4 | Site Plan - section page
| No Edit function to set pan and zoom (done from facility page) | yes
| Shades the selected roof section | yes
| BUG: On section level, if map zoom position is not set, set default to facility zoom level and position | yes
2.5 | Roof Plan - section page
Edit Window:
| Displays Create Roofplan, Edit roofPlan, Save and Cancel | yes
| These first 2 buttons are toggle buttons | yes
| Save to update all changes - position, zoom and polygons | yes
| Cancel to discard all changes to position and polygons | yes
Drawing functions
No changes
| BUG: During creation of roof plan, click Cancel. Drawing tool is still active. What behaviour does it need to have? | yes
| BUG: On Cancel return back to original position | yes
2.6 | Discussion Points
| Should the small maps allow pan, zoom? | No
| Should the zoomed zite plan allow layer select? | NO
3 | Base System Completion | 10
3.1 | General |  | Affilia | EBS
Data entered on Canceled form is retained on next edit
| The required red asterisk should not show on the view form |  |  | Codes
| Do uploads remove storage for any previous uploads? |  |  |  | Minor items/ fixes |  | 4 Hours | 43 items - for Monday
| All photos should display without scroll bars |  |  |  | Additional |  | 6 Hours | 13 items - for Tuesday
| All photos should retain aspect ratio - fixed width, variable height |  |  |  | Future
Changed names don't update to tree
Change "Submit" to "Save" when used on an Add or Edit form
Notes
3.2 | Developer Menu |  |  | To save time - I can assist with testing
| Change menu name to "Developer" |  |  | Notes can added beside each task - Using the Excel Review - New Comment
| Remove "Database Tables" from Developer menu |  |  | Add the note in the coloured cells, as done in first cell.
3.3 | Tree, Add, Delete |  |  | LEGEND
| Remove the title on top border "Aegis Building..." |  |  |  | - Defects and small fixes - 5 hours
| Change to support multiple consultants - multiple root nodes |  |  |  | - Optional, spend 5 hours
| Expand on the arrow prefix only - not on the name |  |  |  | - Future
Fix error handling
Options are unclear - retry vs cancel
Displays dimmed box after cancel
Can drop out of application
Add Segment
Validate as Unique
Add Client:
Add Client not working (Pg 16)
Validate client name unique across all segments
Validate Brief name unique across all segments
Add Facility:
Add Facility not working (Pg 16)
Validate Facility name unique within the client
Validate Facility brief name unique within the client
Add Section
Designation as single line text box
Validate Designation unique within the facility
Change roof name to text input, not select (duplicates allowed)
Delete function
Add to right of Add button
Delete Segment, Client, Facility and Section (not business)
Delete Confirm
Don't allow delete if child records present
3.4 | Business - Summary
Remove edit button (Company information will be maint using QB)
Commas in sq ft
Currency to 0 dec
3.5 | Business - Segments
Remove form at bottom - display when grid line clicked
Commas in sq ft
Commas in currency
3.6 | Business - Map
Remove (after summary page maps working)
3.7 | Segment - Summary
Commas in sq ft
Currency to 0 dec
3.8 | Segment - Clients
Remove form at bottom - display when grid line clicked
Commas in sq ft
Commas in currency
Revise columns
3.9 | Segment - Map
Remove (after summary page maps working)
3.10 | Clients- Summary
Commas in sq ft
Currency to 0 dec
Complete the client View/ Edit form (design 5.7)
3.11 | Client - Facilities
Remove form at bottom - display when grid line clicked
Revise columns
3.12 | Client - Map
Remove (after summary page maps working)
3.13 | Facility - Summary
Additional contacts is editable while in view mode.
Upload error hung the app.
The orange 'in progress' bar didn't go away after upload
3.14 | Facility - Sections
Remove form at bottom - display when grid line clicked
3.15 | Facility - Map
Remove (after summary page maps working)
3.16 | Facility - Siteplan
Remove (after summary page maps working)
3.17 | Facility - Details tab through Warranties tab
Implement as in Design document
3.18 | Facility - Reports
Move the button to the Summary page - Left side - same line as Edit
Remove the Reports tab
Test the condition report content
Test condition page ejects and orphan control
Enhance to support RTF
Enhance to support maps, siteplans and roof plans
Fix the IE problem
Fix the problem on Alistair's computer
3.19 | Section - Summary
Edit form
Sq Ft - numeric input only - remove incr/ decrement
Year Installed - remove incr/ decrement
3.2 | Section - Site Plan
Remove (after summary page site plan working)
3.21 | Section - Roof Plan
Remove (after summary page roof plan working)
3.22 | Section - System
Core Composition Edit form
Double the width of all input controls
Change description to one line
Core Photos Input form
"Layer type" label --> Date taken
Problem in Edit when a new photo is not uploaded
Delete to remove photo storage
Lost cursor - ok on Intuit menu, not our menu or below!
Overall Core Assement memo
No edit function
3.23 | Section - Core Cuts
Remove
3.24 | Section - Details
Implement as in Design document
3.25 | Section - Deficiencies
Implement as in Design document
3.26 | Section - Inspections
Edit Form
Change Inspector Company to Text box, not select
Double the width and height of the assessment memo
Submit didn't respond on Edit form. Cancel worked
Changes not updated - Grid shows prev date.
List in reverse date sequence (latest inspections at top of list)
3.27 | Section - Surveys
Implement as in design document
3.28 | Section - Expenditures
Add/Edit Form
Remove incrementor on budget year
Double the width and height of the details of activity memo
Submit didn't respond (same as inspections)
Error on Type of Activity - Too long (I selected one of the values!)
Edits not saved - same as inspections
3.29 | Section - Warranties
Implement as in Design document
3.3 | Analysis Menu
Implement as in Design document
4 | Inspections | 10
iPhone data capture
Get authenticate and API_AddRecord working (Affilia)
Establish iPhone software delivery process
Test IPP authenticate and upload from iPhone
Test voice, photo and GPS upload
Complete 2-3 prototype designs
Inspection page
Revise inspection fields -as in design spec
Photo upload and annotation entry
Marker placement
Pro-Spec report
Code the report - as in design specs
Dictation
Flex payback with foot pedal
5 | Roles, permissions, user management | 4
6 | Deployment, entitlements, pricing | 4
7 | Future
Aegis Data conversion
Tasks
Note on I22: Jim Maybee: affilia to fix
Note on I23: Jim Maybee: this is a big asd asd asd asdasdasd asd asd asd asd ad asd asd asd
Note on I24: Jim Maybee: Major problem
Note on D32: What does it mean based on property?
Note on D34: No info windows in summary screen
Note on D80: Jim Maybee: Same note

## Sheet2
Usage Notes
- Tasks created for all work done by Affilia.
- All hours billed through time sheets to include the task number.
- Project status to be updated